## Slide 1: BBA 3rd SEM Session(2023-2024) Operations Research
Submitted By-
Shankh Bansal
AU22C1013
Submitted To-
Dr Prachi Vasant

## Slide 2: Q1) The utility data for a network are given below. Determine the total, free, independent and interfering floats and identify the critical path.
Activity | Duration
0-1 | 2
1-2 | 8
1-3 | 10
2-4 | 6
2-5 | 3
3-4 | 3
3-6 | 7
4-7 | 5
5-7 | 2
6-7 | 8

## Slide 3: Q1 - Matrix
Activity | Duration | Earliest Start(ES) | Earliest finish(EF) | Latest Start(LS) | Latest Finish(LF) | Total Float(TT) (LF – LS) | Free Float(FF) (TT – Head value slang) | Independent Float (FF – Tail value slang) | Intensive Float (TF –FF)
0-1 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
1-2 | 8 | 2 | 8 | 10 | 16 | 6 | 0 | 0 | 6
1-3 | 10 | 2 | 2 | 12 | 12 | 0 | 0 | 0 | 0
2-4 | 6 | 10 | 16 | 16 | 22 | 6 | 0 | 0 | 6
2-5 | 3 | 10 | 22 | 13 | 25 | 12 | 0 | 0 | 0
3-4 | 3 | 12 | 19 | 15 | 22 | 7 | 1 | 1 | 6
3-6 | 7 | 12 | 12 | 19 | 19 | 0 | 0 | 0 | 0
4-7 | 5 | 16 | 22 | 21 | 27 | 6 | 6 | 0 | 0
5-7 | 2 | 13 | 25 | 15 | 27 | 12 | 12 | 0 | 0
6-7 | 8 | 19 | 19 | 27 | 27 | 0 | 0 | 0 | 0

## Slide 4
0
1
2
5
4
3
6
7
12
12
27
27
22
16
25
13
16
10
2
2
O
0
19
19
2
7
5
3
8
10
6
8
2
Q1 - Network Diagram
3
Earliest start
Latest finish
Slang value
0
0
0
0
0
12
6
6

## Slide 5: Q2) A project comprising 8 tasks (A to H) has as the following characteristics:
(a) Calculate the time duration of each activity and the variance.
(b) Draw the network diagram, determine the critical path and mark it in the network. What is the total project duration ?
(c) What is the probability of achieving the project completion with the deadline of 30 weeks?
Task | Predecessor | Optimistic | Most likely | Pessimistic
A | - | 2 | 4 | 12
B | - | 10 | 12 | 26
C | A | 8 | 9 | 10
D | A | 10 | 15 | 20
E | A | 7 | 7.5 | 11
F | B,C | 9 | 9 | 9
G | D | 3 | 3.5 | 7
H | E,F,G | 5 | 5 | 5

## Slide 6: Q2 - Matrix
Activity | Optimistic time | Most likely time | Pessimistic time | Duration (OT+4MLT+PT/6) | Variance (PT-OT/6)2
O-A | 2 | 4 | 12 | 5 | 2.7
O-B | 10 | 12 | 26 | 14 | 7.1
A-C | 8 | 9 | 10 | 9 | 0.11
A-D | 10 | 15 | 20 | 15 | 2.7
A-E | 7 | 7.5 | 11 | 8 | 0.44
B-F | 9 | 9 | 9 | 9 | 0
C-F | 9 | 9 | 9 | 9 | 0
D-G | 3 | 3.5 | 7 | 4 | 0.44
E-H | 5 | 5 | 5 | 5 | 0
F-H | 5 | 5 | 5 | 5 | 0
G-H | 5 | 5 | 5 | 5 | 0

## Slide 7
0
B
14
Q2 - Network Diagram
A
C
D
E
F
G
H
9
5
2
2
5
15
4
5
8
5

## Slide 8
Total Project length = 29 weeks
Z = Given project length – Total project length / Project length Standard Deviation
Z = 30 – 29 / 2.18
Z = 0.41
Z value = 0.659
Project length variance = Variance of(A+D+G+H)
Project length variance = 2.7+2.7+0+0.44
Project length variance = 5.84
Critical Path = O-A-D-G-H
Project length standard deviation = √ Project length variance
Project length standard deviation = √5.84
Project length standard deviation = 2.41
The possibility of the project to be completed in 30 weeks is 65.9%
Q2

## Slide 9: Q3) The table below gives the list of activities along with predecessors and three-line estimates is weeks
(a) Draw the project network.
(b) Find the critical path.
(c) Find the probability of completion in 21 weeks and 25 weeks.
Activity | Predecessor | Optimistic time | Most likely time | Pessimistic time
A | - | 1 | 2 | 9
B | A | 2 | 3 | 4
C | A | 2 | 4 | 6
D | A | 3 | 5 | 7
E | C | 5 | 7 | 9
F | D | 1 | 3 | 5
G | B | 1 | 4 | 7
H | G | 2 | 6 | 10
I | E,H | 4 | 8 | 6
J | F | 2 | 6 | 10

## Slide 10: Q3 - Matrix
Activity | Optimistic time | Most likely time | Pessimistic time | Duration | Variance
O-A | 1 | 2 | 9 | 3 | 1.77
A-B | 2 | 3 | 4 | 3 | 0.11
A-C | 2 | 4 | 6 | 4 | 0.44
A-D | 3 | 5 | 7 | 5 | 0.44
C-E | 5 | 7 | 9 | 7 | 0.44
D-F | 1 | 3 | 5 | 3 | 0.44
B-G | 1 | 4 | 7 | 4 | 1
G-H | 2 | 6 | 10 | 6 | 1.77
E-I | 4 | 8 | 6 | 7 | 0.11
H-I | 4 | 8 | 6 | 7 | 0.11
F-J | 2 | 6 | 10 | 6 | 1.77
I-J | 0 | 0 | 0 | 0 | 0

## Slide 11
0
A
C
E
I
J
F
D
B
G
H
3
3
4
4
6
7
7
7
6
3
5
Q3 - Network Diagram
0
Dummy line

## Slide 12
Total Project length = 23 weeks
Z = Given project length – Total project length / Project length Standard Deviation
Z = 21 - 23 / 2.18
Z = -0.91
Z value = 0.1814
Project length variance = Variance of(A+B+G+H+I+J)
Project length variance = 1.77+0.11+1.77+1+0.11+0
Project length variance = 4.76
Critical Path = O-A-B-G-H-I-J
Project length standard deviation = √ Project length variance
Project length standard deviation = √4.76
Project length standard deviation = 2.18
The possibility of the project being completed in 21 weeks is 18.1%
Z = Given project length – Total project length / Project length Standard Deviation
Z = 25 - 23 / 2.18
Z = 0.91
Z value = 0.8186
The possibility of the project being completed in 25 weeks is 81.8%
Q3